## 📋 Sales Import
GMD PRO · FABHUB SMART IMPORT — Sales & Projects
Fill in from Row 4 onwards. Required fields are marked *. For AWARDED projects also fill the green columns (N–T). Delete this row and Row 3 before importing.
DEAL INFORMATION | [12 empty] | AWARDED PROJECTS ONLY (fill if stage ≥ 06)
CE No * | CE Type * | Client Name * | Project / Product * | Stage * | Contract Value | Sales Owner * | Assigned AE | BizDev Source | Date Acquired * | Due Date | Contact Person | Notes | Award Trigger | Trigger Date | Start Date | JO No | AE Assigned (JO) | Comms Group | Payment Status
CE-2026-001 | Fabrication / General | SM Retail Inc. | Custom Shelving – SM North EDSA | 04 · Design & CE in Progress | 750000 | Mar | Mar | Referral – Jun | 2026-01-10 | 2026-02-28 | Ana Reyes | Scope includes gondola shelving x 40 units | [6 empty] | Unpaid
CE-2026-002 | Fabrication / General | Robinsons Malls | Kiosk Installation – Galleria | 08 · Fabrication / Construction | 1200000 | Paulo | Paulo | Direct — Paulo | 2026-01-05 |  | Ben Cruz | Fast-track, target completion April | Contract Signing | 2026-01-20 | 2026-01-27 | JO-2026-001 | Mar | GMD Galleria GC | Partial
CE-2026-003 | Interior Design | Ayala Malls | F&B Fit-Out – TriNoma | 02 · Client Engagement | 500000 | Anna | Anna | Cold Call | 2026-01-18 | 2026-03-15 | Tina Lim | Awaiting brief from client

## 📖 Instructions
FABHUB SMART IMPORT · Field Guide
Column | Field Name | Description | Example / Valid Values | Required?
A | CE No | Your internal cost-estimate reference number. | CE-2026-001 / CE-2026-045 | YES
B | CE Type | Category of the project. | Fabrication / General ¦ Interior Design ¦ Renovation ¦ Signage ¦ Fit-Out ¦ Other | YES
C | Client Name | Company or person name of the client. | SM Retail Inc. / Robinsons Malls | YES
D | Project / Product | Short description of what is being built. | Custom Shelving – SM North EDSA | YES
E | Stage | Current pipeline stage. Use the exact stage name OR just the number (e.g. '05'). | 01 · BizDev … 13 · Client Feedback ¦ Cancelled | YES
F | Contract Value | Total contract amount in PHP. Numbers only, no commas or peso sign. | 850000 | No
G | Sales Owner | First name of the AE responsible for this deal. | Mar / Paulo / Anna | YES
H | Assigned AE | Account Executive name (usually same as Sales Owner). | Mar | No
I | BizDev Source | How was this lead generated? | Referral – Jun / Cold Call / Walk-in / Direct – Paulo | No
J | Date Acquired | Date the lead was first entered. Format: YYYY-MM-DD | 2026-01-15 | YES
K | Due Date | Deadline for proposal or decision. Format: YYYY-MM-DD | 2026-03-01 | No
L | Contact Person | Name of client point-of-contact. | Ana Reyes | No
M | Notes | Any free-text notes about the deal. | Scope TBD pending lease approval | No
N | Award Trigger | AWARDED ONLY. What document triggered the project award? | Contract Signing ¦ PO Issuance ¦ LOI ¦ Verbal Award | No
O | Trigger Date | AWARDED ONLY. Date the award trigger was signed/issued. YYYY-MM-DD | 2026-02-10 | No
P | Start Date | AWARDED ONLY. Actual on-site or fabrication start date. YYYY-MM-DD | 2026-02-17 | No
Q | JO No | AWARDED ONLY. Job Order number assigned to this project. | JO-2026-001 | No
R | AE Assigned (JO) | AWARDED ONLY. AE assigned on the Job Order. | Mar | No
S | Comms Group | AWARDED ONLY. Name of Viber/Telegram group chat for this project. | GMD Galleria GC | No
T | Payment Status | Current payment status of the project. | Unpaid ¦ Partial ¦ Paid | No

## ✅ Valid Values
FABHUB SMART IMPORT · Valid Values Reference
STAGE (Column E)
01 · BizDev | Lead identified, no contact yet
02 · Client Engagement | First meeting / calls ongoing
03 · Design Request & Folder Setup | DRF submitted, folder created
04 · Design & CE in Progress | CE being prepared
05 · Client Approval / Revision | CE sent, waiting for sign-off
06 · Project Kickoff | AWARDED — project starts
07 · Budget & Briefing | Internal budget finalized
08 · Fabrication / Construction | On the floor / on-site
09 · Site Visit & Progress Billing | Billing milestone reached
10 · Installation | Items being installed
11 · Punchlist | Defects / snag list
12 · Project Close-Out | Turnover / COC signed
13 · Client Feedback | Post-project survey
Cancelled | Project cancelled
CE TYPE (Column B)
|  | Fabrication / General | Custom furniture & millwork
|  | Interior Design | Design-only or design-led project
|  | Renovation | Fit-out of existing space
|  | Signage | Signage and branding installation
|  | Fit-Out | Full retail / commercial fit-out
|  | Other | Anything else
AWARD TRIGGER (Column N)
|  | Contract Signing | Signed contract document
|  | PO Issuance | Purchase Order from client
|  | LOI | Letter of Intent
|  | Verbal Award | Verbal go-signal (follow up with PO)
PAYMENT STATUS (Column T)
|  | Unpaid | No payment received yet
|  | Partial | Down payment or partial billing paid
|  | Paid | Fully paid
|  | Refunded | Payment returned to client